## Board Report
Citation Number: | Owner/Permittee | Property Address: | Violation | CO Executed | Update (DateDue/ Item/ Date Received) | Referred to OGC
ASB-26-04 | Diego Francisco Rodrigues Mora and Linder Lopez Mendoza | 5349 Lenox Ave | Demolition or renovation of an installation without prior notification to the City of Jacksonville Environmental Quality Division and the Florida Department of Environmental Protection (DEP) is a violation of JEPB Rule 2.201 [which adopts the National Emission Standards for Hazardous Air Pollutants (NESHAP), including 40 Code of Federal Regulations (CFR) 61.145(b), by reference, through Florida Administrative Code (FAC) Rule 62-204]. | 2026-10-19 | - 11/18/2026 Due: Penalty payment only
NP-26-17 | Savier Stephens | 6843 N Pearl Street | Causing, allowing, or permitting emission of sound to Class B receiving land in exceedance of noise limits | 2026-09-28 | - 10/27/2026 Due: Penalty Payment Only
ASB-26-05 | Hodges Boulevard Presbyterian Church, Inc.; Patriot Contracting of CF, LLC | 4140 Hodges Blvd | Demolition or renovation of an installation without prior notification to the City of Jacksonville Environmental Quality Division and the Florida Department of Environmental Protection (DEP) is a violation of JEPB Rule 2.201 [which adopts the National Emission Standards for Hazardous Air Pollutants (NESHAP), including 40 Code of Federal Regulations (CFR) 61.145(b), by reference, through Florida Administrative Code (FAC) Rule 62-204]. | 2026-09-28 | - 10/27/2026 Due: Penalty payment only
AP-26-07 | Felizardo Investments, LLC | 0 Southern Ave | JFRD responded to a call about open burning on the listed property during a Duval County Burn Ban. | 2026-09-28 | - 10/27/2026 Due: Penalty payment only - updates
ESC-26-01 | Hawk Normandy LLC, Hawk Land Investors New, LLC, Smith Trucking Company, Inc. | 0 Forest Trail Road | Discharge of turbid water, Failure to install and maintain adequate turbidity controls | 2026-09-28 | - 10/27/2026 Due: Penalty payment only
ESC-26-04 | Eagles Glen, LLC; Dream Finders Homes LLC; Smith Trucking Company, Inc. | 0 POW-MIA Memorial Parkway | Discharge of non-stormwater to City municipal separate storm sewer system (“MS4”); Failure to comply with erosion and sediment control requirements. | 2026-08-17 | - 9/17/2026 Due: Penalty payment only 9/2/2026 - 9/2/2026 Case Closed
NP-26-12 | Ability Park Place, LLC; GFL Solid Waste Southeast LLC | 2765 Park Street, |  | 2026-08-17 | - 9/16/2026 Due: Penalty payment only 9/15/2026 - 9/17/2026 Case closed
NP-26-13 | Richard Williams; GFL Solid Waste Southeast LLC | 12134 Fort Caroline Road | Refuse Service-Dumpster Collection-No person shall operate or permit the operation of any trash or refuse service, using a mechanical device for unloading a bin or hopper into a truck, during nighttime hours, within 200 meters of a property that is in a Class A or Class B area, unless a Nighttime Dumpster Collection Permit has been granted by the Board, in accordance with “D” of this subpart. | 2026-08-17 | - 9/16/2026 Due: Penaly payment only
WP-24-17 | Regency Plaza Partners LLC | 9840 Atlantic Boulevard | Discharge of untreated wastewater to the ground, | 2026-06-15 | - 5/30/2026 Due: Monthly Status Report 5/13/2026 - 5/30/2026 Due: Monthly PS Report 5/13/2026 - 7/14/2026 Due: Penalty payment 7/9/2026 - 8/15/2026 Due: Initial engineer report - 10/15/2026 Due: Final Engineer Report - HG sent reminder email for status. Past due 9/21/2026
WP-25-37 | 3200 Armsdale LLC | 3200 Armsdale Road | Unpermitted Discharge of untreated wastewater to the ground, MS4, and surrounding environment; failure to notify EQD of Discharge from the System; no compliant sign at the time of the inspection | 2026-03-16 | - 4/15/2026 Due: Penalty payment 3/20/2026 - 4/15/2026 Due: Education Campaign 4/14/2026 - 4/30/2026 Due: Monthly Status Report 4/14/2026 - 5/30/2026 Due: Monthly PS Report 5/29/2026 - 5/30/2026 Due: Initial Engineer Report -extended 5/15/26 5/29/2026 - 6/29/2026 Due: Joe E. review pending- 5/29/2026 - 7/15/2026 Due: Final Engineer Report
WP-25-30 | Szabo Trust | 253 State Street E, | Wastewater was allowed to discharge to the ground and surrounding environment; EQD was not notified of the wastewater discharge; no compliant sign was posted at the pump station; the valve box was not secured. | 2026-02-17 | - 3/16/2026 Due: Penalty payment 3/13/2026 - 5/30/2026 Due: Monthly Status Report 5/22/2026 - 5/30/2026 Due: Monthly PS Report 5/12/2026 - 8/21/2026 Due: Initial engineer report-ext 6/15, 8/1 - 10/16/2026 Due: Final Engineer Report
WP-25-28 | Ryans Pond Property Homeowners Association Inc | 6547 (0) Sweetbay Lane, | Sewage was allowed to discharge to the ground and surrounding environment; Sewage was allowed to discharge to the stormwater infrastructure; EQD was not notified of the ongoing sewage discharge | 2026-01-20 | - 2/20/2026 Due: Penalty payment 2/4/2026 - 2/20/2026 Due: Education Campaign 4/20/2026 - 3/27/2026 Due: Initial Engineer Report (IER) 3/24/2026 - 10/25/2026 Due: Final Engineer Report Review - 10/25/2026 Due: Pending surge protection installation
WP-25-33 | Caroline Square Realty LLC | 5959 Fort Caroline Road | Sewage discharge to ground and stormwater; failure to notify | 2026-01-20 | - 3/20/2026 Due: Penalty Payment 3/10/2026 - 5/15/2026 Due: Education Campaign_not received 2/20/26 5/11/2026 - 7/20/2026 Due: Engineer Report_3/20/2026
WP-25-35 | Kendall Court LLC; Kendall Court Realty LLC | 10535 Lem Turner Road | Wastewater discharge to ground, stormwater; pump station failure | 2026-01-20 | - 2/20/2026 Due: Penalty payment 2/5/2026 - 2/20/2026 Due: Education Campaign 2/17/2026 - 12/19/2025 Due: Engineer Report Review 1/12/2026 - 3/1/2026 Due: Install 2 new Tsurumi 80C27.5-CR, 10HP, 230V, 3-Phase, Reconfigure the wet well control floats, refer to email 2/17/2026 - 4/1/2026 Due: Remote cellular annunciator system 2/17/2026 - 10/15/2026 Due: Completion of Action Items in ER report see email
WP-25-20 | Magnolia Point CGC LLC | 7507 Beach Blvd | Wastewater was allowed to discharge to the ground and surrounding environment; EQD was not notified of the wastewater discharge; A wire was coming from under the wet well lid; The system was modified without a permit, including, but not limited to, a new pump operating separate from the original system. | 2026-01-20 | - 2/20/2026 Due: Penalty Payment 3/3/2026 - 4/4/2026 Due: Education Campaign 3/6/2026 - 3/27/2026 Due: Completion dates for the actions recom by Joe 3/26/2026 - 4/3/2026 Due: Emailed Bob Philips for actions due dates 4/9/2026 - 7/20/2026 Due: Final Engineer Report
AP-25-01-VCP | City of Atlantic Beach | 1100 Sandpipe Lane | Objectional Odors | 2025-09-15 | - 12/31/2025 Due: Monthly Status Report Updates 12/18/2025 - 1/30/2026 Due: Monthly Status Report Updates Jan 2026 1/23/2026 - 2/28/2026 Due: Monthly Status Report Updates Feb 2026 2/23/2026 - 3/30/2026 Due: Monthly Status Report Updates Mar 2026 3/11/2026 - 4/30/2026 Due: Monthly Status Report Updates Apr 2026 - 5/30/2026 Due: Monthly Status Report Updates May 2026 - 7/30/2026 Due: Final Completion
WP-25-19 | Tagg Ventures, LLC | 5638 Commonwealth Avenue | No compliant sign was posted at the pump station;The audible visual alarms had malfunctioned and there was no generator receptacle, lightning protection, phase protection, or estimated time meters for each pump; The pump station was only equipped with one pump; The electrical component and wet well were not secured. | 2025-09-15 | - 6/30/2026 Due: Engineer Report - extended Bob P. 1/11/2026 6/30/2026 - 7/15/2026 Due: Comments from Joe E.
WP-24-25 | Cyclone Cross Creek Owner LLC | 1441 Manotak Avenue | Discharge of untreated wastewater to the ground, surrounding environment and stormwater system; Failure to comply with Wastewater Collection/Transmission System design standards; Failure to notify EQD of Discharge from the System; and Failure to provide required records. | 2025-08-18 | - 9/15/2025 Due: August Monthly Status Updates - 9/15/2025 Due: August PS Monthly Maint Reports - 10/15/2025 Due: September Monthly Status Updates - 10/15/2025 Due: September PS Monthly Maint Reports - 9/18/2025 Due: Education Campaign - 10/18/2025 Due: 60 days – Initial Engineering report - 12/18/2025 Due: Final Engineer Report - 9/18/2025 Due: Civil fine requested wire transfer 9/20/2025 - 12/8/2025 Due: Civil fine extended - 2/13/2026 Due: Updated PS records 2/7/2026 - 6/26/2026 Due: Updated PS records March-May 2026
WP-23-64 | PRCP St. Johns Forest LLC | 7925 Merrill Rd | Sewage was allowed to discharge to the surrounding environment | 2024-10-21 | - 11/20/2024 Due: Payment 11/13/2024 - 11/20/2024 Education Campaign 11/26/2024 - 2/20/2025 Initial Engineer Report 5/1/2025 - 10/30/2025 Final Engineer Report[initial rpt rec'd 5/1/25] - Permit Application - replacing PS 8/25/2025 - RAI sent 9/9/2025 - 1/20/2026 Due: Permit issurance update from JEA 2/4/2026 - 3/12/2026 Due: Construction for closure 5/5/2026 - 5/30/2026 Due: Eng Report review by Joe E. 5/30/2026 - Due: signed COC application, PS start-up, etc 7/21/2026 - 8/15/2026 Due: Closure
WP-24-20 | FLI Properties LLC | 2143 Edgewood Ave W | Discharge of untreated wastewater to the ground, surrounding environment and stormwater system; Failure to operate and maintain the System to remain operational; Failure to comply with Wastewater Collection/Transmission System design standards; Failure to perform required maintenance; and Failure to provide required records | 2024-07-15 | - 8/15/2024 Due: Payment 8/20/2024 - Facility submitted proposal for Eng Eval for approval 9/11/2024 - Prelim Eng report submitted 11/26/2024 - 12/15/2024 Due: Final Engineer Report or DEP clearance documents [not received] 12/15/2024 - Email sent to remind Popeye's of engineering report due date 2/3/2025 - 2/28/2025 Due: Final Engineer Report or DEP clearance documents (not submitted) 4/18/2025 - Email sent to get update on engineering report 4/18/2025 - 4/25/2025 Due: Status Report on Eng 4/22/2025 - 6/30/2025 Due: Civil Plans from AVA Eng provided an update 5/19/25 -extended 6/30/2025 - FDEP permit approved 6/19/2025 - 9/1/2025 Due: Construction completion report - 8/2/2025 Due: PS May-July 8/14/2025 - 9/23/2025 Due: PS August 9/19/2025 - 10/5/2025 Due: PS Sept 10/22/2025 - 11/5/2025 Due: PS October 12/22/2025 - 12/5/2025 Due: PS November 12/22/2025 - 12/31/2025 Due: PS December 12/22/2025 - 1/20/2026 Due: SR December - 2/5/2026 Due: PS January - HG asked for an update 9/21/2026 - WindRiver advised property has sold, but this is not supported in Duval County Clerk of Court or Property Appraiser - 10/2/2026 Due: Vorpe working on follow-up docs 9/22/2026
WP-23-53 | Rose Creek Condominium Association Inc. | 1604 Arcadia Drive (RE #099199-0501) | Discharge of untreated wastewater to the ground, surrounding environment and stormwater draining to MS4; Failure to comply with Wastewater Collection/Transmission System design standards; Failure to notify EQD of Discharge from the System and Failure to provide required records | 2023-10-23 | - Email reminder sent about status update and PS Monthly Maintenance due 10/30/2023 - Preliminary Eng Report submitted - waiting on approval at meeting to accept as the Engineering recommendations 11/28/2023 - Email sent to clarify engineering submittal to review 2/15/2024 - 8/29/2025 Due: Response to email requesting confirmation of completion of work and invoices to be submitted 8/29/2025 - 6/15/2026 Due: Contractor selection and funding approval - 8/15/2026 Due: Contract execution and scheduling - 10/15/2026 Due: Engineer Report extended HOA issues 12/22/23 - -
WP-23-47 | Q and H LLC | 5161 Beach Blvd | Discharge of untreated wastewater to the ground, surrounding environment and stormwater draining to MS4; Allowing untreated wastewater into the storm sewer system; Failure to notify EQD of Discharge from the System and Failure to provide required records; Failure to provide safe, dry access to the Pump Station; Failure to perform required maintenance; and Failure to provide required records | 2023-09-25 | - 9/26/2023 Due: Engineer Report 9/26/2023 - Pumps have been replaced, control panel replaced. PS will be monitored for one year to ensure good operation 9/26/2023 - 1/31/2024 Due: explanation about pump 2 and missing PS reports 1/18/2024 - 12/30/2025 Due: PS 2025
ESC-22-50 | Aireit Commonwealth Logistics Center LLC; Inlight Real Estate Acquisitions, LLC; and Dana B. Kenyon Company | 0 Imeson | Discharge of non-stormwater to MS4 and wetlands draining to Waters; Failure to comply with erosion and sediment control requirements | 2022-11-21 | - 12/21/2022 Due: Penalty 12/7/2022 - Site will be monitored periodically until final stabilization
WP-22-43 | JJTA13 Real Properties LLC | 6253 and 6259 Wilson Blvd. | Discharge of untreated wastewater to the ground and surrounding environment draining to Waters; Failure to operate and maintain the System to remain operational, to function as intended, and to provide uninterrupted transmission of wastewater; Allowing wastewater to bypass the System or its Treatment Facility; Failure to notify EQD of Discharge from the System and provide required records | 2022-10-24 | - Referred to OGC for non-compliance with CO 2/1/2023 - Working with facility to get all documents submitted and set interim deadlines for progress - 6/17/2024 Due: update on engineer selection or plumber for this service - 11/14/2024 Due: update on status - did not receive 11/14/2024 - Due: Request to Petition to Enforce 2/7/2025 - 4/11/2025 Due: Update from Erin - Requested facility update from Vanessa Reid 10/29/2025 | yes
WP-22-19 | Catalina Residences TIC I, LLC (30.37%), Catalina Residences TIC II, LLC (28.74%) and Catalina Residences TIC III, LLC (40.89%) | 1033 Bert Rd. | Unlawful discharge of untreated wastewater to the ground and surrounding environment; Failure to operate and maintain WWCTS with Pump Station to function as intended and to provide uninterrupted service; Unlawful bypass of the System or treatment facility; Failure to notify EQD of discharge of wastewater from the System | 2022-10-24 | - 12/23/2022 Due: Engineer Report - extension granted 6/24/2023 - 5/31/2023 Due: Engineer Report 6/24/2023 - 4/19/2024 Due: Status Update on Eng. recommendations and confirmation of monthly operator 4/19/2024 - 7/31/2024 Due: Requested petition to Enforce 1/14/2025 - 1/16/2025 Due: follow up from attorney 1/16/2025 - Emailed facility to claify 1033 Bert (pump station) vs 840 Bert (gravity through cleanout caps) 4/3/2025 - 4/11/2025 Due: EM response to ML status update - attorney sent proposal from Consolidated but no contract 4/9/2025 - OGC had conversation with Dempsey (attorney) to request update on pump station issues 4/15/2025 - 4/16/2025 Due: update on pump station issues [no response] 4/16/2025 - 7/31/2023 Due: Repair Interior flow benches in MH1 and 6 - 7/31/2023 Due: Install new sign - 7/1/2023 Due: replace sewer clean-out caps - 10/22/2023 Due: New pump station - 2/12/2024 Due: Status Update on Eng. recommendations - 6/24/2024 Due: Last attempt on updates before referring to OGC - Due: Installation of compliant sign - Due: Repairs to interior flow benches in manholes 1 & 6 - Due: Remove & replace existing pump station, & other items - Due: Install compliant control panel - 5/16/2025 Due: Response to OGC counter-offer for pump station repairs - Followed up on Joe's request for info 11/4/2025 | yes
WP-22-22 | A & S Hospitality Group LLC | 510 Lane Ave | Unpermitted Discharge of untreated wastewater to the ground and surrounding environment; Failure to operate and maintain WWCTS with Pump Station to remain operational, to function as intended, and to provide uninterrupted transmission of wastewater; Allowing stormwater to enter into a sewer designed to carry wastewater; Allowing wastewater to bypass the System or its Treatment Facility; Failure to comply with WWCTS design standards; Failure to perform required maintenance at the System and/or have required records; Failure to notify EQD of Discharge from the System and provide required records | 2022-08-15 | - 9/30/2022 Due: Engineer Report [no response] 4/29/2025 - Engineer previously advised to replace grease trap, clean lines and then he would update report. 11/30/2022 - Sent engineer email asking for update 4/24/2023 - Sent engineer email asking for update 2/5/2024 - Email sent with new deadlines 8/1/2024 - 8/15/2024 Due: Select Engineer [no response] 8/15/2024 - 9/30/2024 Due: Engineer Report [no response] 4/29/2025 - Sent engineer email asking for update with new deadline Due:1/31/2025 1/28/2025 - 2/14/2025 Due: Engineer selection (none selected yet) 4/17/2025 - ML requested status update. 4/29/2025 - 5/2/2025 Due: Response about engineer (email sent summary below) 4/29/2025 - Damney discussed efforts with grease traps and will be calling engineers soon 4/29/2025 - Damney stated in her email the control panel was replaced and the grease trap was repaired. 4/29/2025 - 5/15/2025 Due: Response about engineer [no response] 7/7/2025 - 7/25/2025 Due: Response about engineer [no response] 11/5/2025 - 11/10/2025 Due: Response about engineer - 5/18/2026 Due: Requested PS records & grease trap 5/18/2026 - 5/28/2026 Due: 12 month PS records (partial) received 5/18/26
WP-22-21 | Leos Liquor Express, Inc. | 904 Edgewood Ave N. | Unpermitted Discharge of untreated wastewater to the ground, surrounding environment and municipal separate stormwater sewer system (“MS4”); Failure to operate and maintain the WWCTS with Pump Station to remain operational, to function as intended, and to provide uninterrupted transmission of wastewater to the Regional Sewer Utility point of connection; Unlawful bypass of the System or its Treatment Facility; Failure to notify EQD of discharge and submit required records | 2022-08-15 | - 10/14/2022 Due: Engineer Report (Bob Phillips had delays - needed extension of time 11/30/2022 - 4/30/2023 Due: Engineer Report [no response] 5/19/2025 - Sent email requesting status update to engineer 2/5/2024 - 12/30/2025 Due: Engineer Report status update-non 5/30/25
WP-22-25 | Double Naught, Inc. | 5351 Normandy Blvd. | Unpermitted Discharge of untreated wastewater to the ground, surrounding environment and MS4; Failure to operate and maintain the System to remain operational, to function as intended, and to provide uninterrupted transmission of wastewater; Allowing wastewater to bypass the System or its Treatment Facility; Failure to comply with Wastewater Collection/Transmission System design standards; Failure to notify EQD of Discharge from the System and provide required records | 2022-08-15 | - 2/28/2023 Due: Permit Application [extended below] 2/28/2023 - Engineer researching gravity option - Follow up with in-house to see if permit application was submitted - staff indicated they spoke with engineer and would be submitting permit next week 5/22/2023 - 1/31/2025 Due: Requested an update from Heather 1/14/2025 - 4/30/2026 Due: COC -quotes upward $200k 10/25/25 - 12/22/2025 Due: PS Jan - Nov 2025 from ASAP - 9/25/2026 HG sent update request 9/21/2026 - 10/2/2026 Due: Cavanagh to submit construction completion form 9/21/2026
WP-21-45 | Malabar Motel and Mobile Home Park LLC | 8375 New Kings Rd. | Unlawful discharge of wastewater to ground and surrounding environment; Failure to maintain WWCTS with lift station; Unlawful bypass of treatment facility; Failure to comply with sewerage design standards; Failure to notify EQD of discharge and provide required records | 2022-04-18 | - 5/18/2022 Due: Penalty 5/17/2022 - Due: Engineer report 4/28/2022 - Email confirmed they found their point of connection to JEA 7/8/2022 - Owner to provide easement for access to this POC 7/8/2022 - EQD met with engineer to discuss steps to complete permit application 7/23/2022 - Waiting on owner to provide easement information - need survey 6/22/2023 - 1/30/2025 Due: PS records Jan 2/10/2025 - 2/28/2025 Due: PS records Feb 2/26/2025 - 3/31/2025 Due: PS records Mar 3/24/2025 - 4/30/2025 Due: PS records Apr 5/9/2025 - 5/31/2025 Due: PS records May 6/12/2025 - 6/30/2025 Due: PS records Jun 7/3/2025 - 7/30/2025 Due: PS records July 8/3/2025 - 9/2/2025 Due: PS records August 8/27/2025 - 10/2/2025 Due: PS records Sept 9/29/2025 - 11/2/2025 Due: PS records Oct 10/31/2025 - 12/2/2025 Due: PS records Nov 11/26/2025 - 1/2/2026 Due: PS records Dec 1/13/2026 - 11/24/2025 ML to determine whether to close executed consent order based on pump station records
VCO-21-01 | JJTA5 Real Properties, LLC | 5537 Firestone Rd. | Failure to comply with sewerage design standards | 2021-04-19 | - 6/18/2021 Due:DEP permit application 10/1/2021 - EQD reminder of deadlines emailed 5/26/2021 - Engineer status report and lift station records received 6/2/2021 - update - Inspection reports 7/30/2021 - DEP Permit issued 10/4/2021 - Collection System permit issued 11/1/2021 - 2/1/2022 Due:Request for Approval/Clearance - Email of noncompliance and stipulated penalties sent 4/13/2022 - No records or reports received by EQD 6/2/2022 - Referred to OGC for Petition to Enforce Consent Order 6/2/2022 - PN:Owner requested I call him while I was out of office, emailed previous email chain 6/28/2022 - Emailed everyone the DEP Permit issued with previous engineer and Approved Consent 10/14/2022 - TDB sent owner contact info to M Long 4/10/2023 - 6/6/2024 Due: for melissa review - 6/17/2024 Due: update on engineer selection - 11/14/2024 Due: update on status -did not respond 11/14/2024 - Request to Petition to Enforce 2/7/2025 - 4/11/2025 Due: Update from Erin 4/15/2025 - 4/22/2025 Due: ML to summarize and set meeting - Requested last year of records 10/29/2025 | yes
WP-21-04 | JJTA6 Real Properties, LLC | 7154 Conant Ave. | Unlawful discharge of wastewater to ground and surrounding environment; Failure to maintain gravity WWCTS; Unlawful bypass of WWCTS treatment facility | 2021-03-15 | - EQD follow-up email for payment and reports sent 4/15/2021 - Final email before stipulated penalties sent 5/19/2021 - Engineer status report received 6/2/2021 - Collection system permit issued 11/1/2021 - Email sent requesting status report 1/7/2022 - 4/30/2022 Due:EQD email sent, engineer report (no response) 4/30/2022 - Notice to Owner of Rule 3 Amendments with Pump Station Inspection Form and, wastewater compliance education with records review spreadsheet emailed to owner 6/2/2022 - No records or reports received by EQD 6/2/2022 - Referred to OGC for Petition to Enforce Consent Order 6/2/2022 - Owner requested I call him while I was out of office, emailed previous email chain with Approved Consent Order and advised this matter had been referred to the City attorneys. 6/28/2022 - Henry Vorpe contacted EQD to advise he was hired to review system. 10/14/2023 - Emailed everyone the DEP Permit issued with previous engineer and Approved Consent Order 10/14/2023 - TDB spoke to Vanessa Reed (COO) she thought this one was closed - 7/7/2023 - Civil fine paid 4/27/2021 & Plumber's report showing no obstructions in the gravity line. 7/9/2024 - 11/14/2024 Due: update on status - did not receive 11/14/2024 - Referred to OGC for Petition to Enforce Consent Order 2/7/2025 - 4/11/2025 Due: Update to Erin/Shannon 4/15/2025 - 4/22/2025 Due: summary of case - Requested facility update from Vanessa Reid 10/29/2025 | yes
WP-21-02 | JJTA3 Real Properties, LLC | 7225 Crane Ave. | Failure to comply with sewerage design standards for WWCTS with lift station; Failure to perform maintenance and/or keep records | 2021-03-15 | - EQD follow-up email for payment and reports sent 4/15/2021 - Engineer status report and lift station records received 6/2/2021 - DEP Permit application received 10/27/2021 - 6/30/2022 DEP Permit issued all work to be completed and DEP Request for Approval submitted 11/16/2021 - Email for noncompliance with Consent Order requirements sent 1/7/2022 - Owner notice for Rule 3 Amendments Owner with required maintenance form emailed 5/10/2022 - No records or reports received by EQD 6/2/2022 - Notice to Owner of Rule 3 Amendments with Pump Station Inspection Form, wastewater compliance education PDF with records review spreadsheet, all emailed to property manager 5/13/2022 - EQD final email sent 6/2/2022 - Referred to OGC for Petition to Enforce Consent Order 7/1/2022 - Owner requested I call him while I was out of office, emailed previous email chain with Approved Consent Order and advised this matter had been referred to the City attorneys 6/28/2022 - EQD and OGC hoping complaint at 7423 Linda Dr. would prompt the JJTA owners to act. Nothing so far - Henry Vorpe contacted EQD to advise he was hired to review system 10/14/2022 - Emailed everyone the DEP Permit issued with previous engineer and Approved Consent Order 10/14/2022 - TDB sent owner contact info to M Long 4/10/23, - 6/22 Vorpe emailed "repairs under construction" 9/5/2023 - Melissa sent email to Vanessa to summarize what is needed. - 6/17/2024 Due: update on engineer selection or plumber for this service - 11/14/2024 Due: update on status -did not respond 11/14/2024 - Due: Request to Petition to Enforce 2/7/2025 - 4/11/2025 Due: Update to Erin/Shannon 4/15/2025 - 4/22/2025 Due: summary of case - Requested facility update from Vanessa Reid 10/29/2025 - Documented subsequent discharge 11/7/2025 | Yes
WP-20-40 | JJTA1 Real Properties, Inc. | 7423 Linda Dr./ 7420 Linda Dr. | Unlawful discharge to ground; failure to maintain WWCTS with lift stations; unlawful bypass of system; failure to notify EQD and provide required records | 2021-01-19 | - 2/15/2021 First status report due 2/15/2021 - 3/18/2021 Engineer Report due 3/18/2021 - EQD follow-up for status report sent 2/18/2021 - EQD follow-up on payment and status report 2/25/2021 - Final email for required records and reporting and to begin process for stipulated penalties sent 4/15/2021 - Engineer status report and lift station records received 6/2/2021 - update - Linda Street Engineering review is progressing, TOPO survey was completed, Work orders have been written for the area that need work to be done. 7/3/2021 - EQD requested documentation of Final Stabilization by email 10/20/2021 - Joe received DEP Permit application likely in lieu of Engineer Report 10/28/2021 - 5/31/2022 DEP Permit issued , all work to be completed and DEP Request for Approval submitted 11/16/2021 - Email for noncompliance with Consent Order requirements sent 1/7/2022 - Owner notice for Rule 3 Amendments Owner with required maintenance form emailed 5/10/2022 - Wastewater compliance education PDF with records review spreadsheet emailed to property owner 6/2/2022 - No records or reports received by EQD 6/2/2022 - Referred to OGC for Petition to Enforce Consent Order. 6/2/2022 - Contractor advised alarms and failures by email and EQD forwarded to T. Bowles to proceed with complaint as soon as possible. 6/14/2022 - Chief Long emailed concurrence 6/14/2022 - Owner requested I call him while I was out of office, emailed previous email chain with Approved Consent Order and advised this matter had been referred to the City attorneys 6/28/2022 - OGC Complaint Filed 6/15/2022 - Summons served 6/20/2022 - No Answer filed. OGC Motion for Default filed 7/21/2022 - OGC and Chief trying to schedule meeting with owner and engineer 7/27/2022 - Discharge documentation emailed to OGC 7/29/2022 - Henry Vorpe contacted EQD to advise he was hired to review system. 10/14/2022 - Emailed everyone the DEP Permit issued with previous engineer and Approved Consent Order 10/14/2022 - Long to follow up on update. TDB sent owner contact info to M Long 4/10/23 -- 6/22 Vorpe emailed "repairs under construction" - 6/6/2024 Due: for melissa review 6/6/2024 - 6/17/2024 Due: update on engineer selection - 11/14/2024 Due: update on status -did not respond 11/14/2024 - Request to Petition to Enforce 2/7/2025 - 4/11/2025 Due: Update to Erin/Shannon 4/15/2025 - 4/22/2025 Due: summary of case - Requested facility update from Vanessa Reid 10/29/2025 | Yes
WP-24-12 | Miramar Residences TIC I, LLC and Miramar Residences TIC II, LLC and Miramar Residences TIC III, LLC | 3016 Justina Rd | Discharge of untreated wastewater to the ground, surrounding environment; Failure to operate and maintain the System to remain operational and Failure to notify EQD of Discharge from the System. |  | - 2/22/2025 Due: Payment (not paid) 3/18/2025 - 2/21/2025 Due: Education Campaign 4/9/2025 - 3/21/2025 Due: Report for jetting and televising lines (not rec'd) 4/25/2025 - 5/30/2025 Due: Payment - 5/30/2025 Due: SR March - 5/30/2025 Due: Report for jetting and televising lines - 1/20/2026 Due: Payment extended again 6/27/25 or OGC