## Table 1
This status report is meant to be used as a guide to the transportation improvements recommended in the University Hills Transportation Study. The planning, scheduling and completion of the recommendations are subject to change based upon weather constraints, fiscal year budgeting and additional considerations.
ENGINEERING RECOMMENDATIONS
RECOMMENDATION | DESCRIPTION | STATUS
A.1 | Add crosswalks to the intersection of Gabrielino Drive/California Avenue, Twain Street/California Avenue, and Gabrielino Drive/Russell Place. | Completed (Need additional crosswalk at Los Trancos and Vista Bonita)
A.2 | Add crosswalk to Gabrielino Drive at East Peltason Drive. | Completed
A.3 | Paint the existing un-controlled mid-block crossing on Vista Bonita Drive. | Completed
A.4 | Add yellow centerline striping at blind corners in the residential enclaves as well as on Gabrielino Drive from California Avenue to Mayer Court. | Completed
A.5 | Adjust the location of limit lines to 1-foot from the edge of the pedestrian landing. | Completed
A.6 | Coordinate with UCI on potentially removing the bike lanes on Gabrielino Drive and Owen Drive to provide on-street parking. | Completed (under review)
A.7 | Add “Stop Ahead” pavement legends on the northbound and southbound direction of Los Trancos Drive at Vista Bonita Drive. | Completed
A.8 | Add stop ahead warning signs at the “Stop Ahead” pavement legends on California Avenue at the intersection with Twain Street and Gabrielino Drive. | Completed
A.9 | Add speed limit sign on Russell Place west of Anteater Drive, on Gabrielino Drive south of East Peltason Drive, and Gabrielino Drive south of California Avenue. | In Progress (to be completed by year's end)
A.10 | Add school zone sign on Russell Place west of Anteater Drive. | In Progress (to be completed by year's end)
A.11 | Adjust the stop sign locations to be at the Beginning of Curb Return (BCR) or at the edge of the pedestrian landing. | In Progress (to be completed by year's end)
A.12 | Install “No Parking” signs on local streets with a width of less than 36 feet. | TBD
A.13 | Develop a periodic landscape trimming program to ensure adequate clearance around signs, streetlights, pedestrian path of travel, and sight distance. Work with homeowners regarding trimming in their yards and develop enforcement procedures. | Under community management supervision
A.14 | Replace landscaping at street corners with low ground cover. | Under community management supervision
A.15 | Remove the stop signs and pavement legends on California Avenue at Mistral Lane, at Whistler Court, and at Eliot Court then to add stop signs and pavement legends at Owen Drive. | Completed
A.16 | Remove the northerly un-controlled mid-block crossing on Los Trancos Drive near the pool. | Completed
A.17 | Install an additional streetlight at the southerly un-controlled mid-block crossing on Los Trancos near the pool. | In Planning Process
A.18 | Install in-pavement flashers with pedestrian push button activation at the southerly uncontrolled mid-block crossing on Los Trancos near the pool. | Future Fiscal Year TBD
A.19 | If the striping changes in Recommendation A.6 are implemented, on-street parallel parking spaces could be provided on Gabrielino Drive adjacent to the park. | Completed (under review)
A.20 | Designate several parking spaces on Twain Street between Bronte Street and Murasaki Street opposite the park to be used during the daytime hours or weekends. | Under review
A.21 | A secondary dog park entrance could be established on Twain Street: This will allow easier access from areas north of the park. | In Planning Process (Community Management is facilitating the dog park improvements)
A.22 | If the striping changes in Recommendation A.6 are implemented, on-street parallel parking spaces could be provided on Owen Drive adjacent to the park. | Completed
A.23 | Designate tennis court/park-only parking spaces on Urey Court adjacent to the tennis court/park during the daytime hours or weekends. | Completed (under review)
A.24 | Conduct a detailed analysis of providing off-street parking adjacent to the Vista Bonita Park. | TBD
A.25 | Obtain input from residents in each phase on whether to implement on-street parking markings. | TBD
A.26 | Install radar speed feedback signs on California Avenue east of Mistral Lane, on Los Trancos Drive at Blake Court, and on Gabrielino Drive opposite Zola Court. | TBD
A.27 | Install transverse markings or optical speed bars at radar speed feedback sign locations. | TBD
A.28 | In Phase 8, install chokers on Twain Street at Bronte Street and at Murasaki Street. In Area 11, install chokers on Pauling Court at Gabrielino Drive, Coltrane Court, and Kahlo Court. | Future Fiscal Year TBD
A.29 | Install an 8-foot shoulder on the westerly side of Gabrielino Drive south of California. | Future Fiscal Year TBD
A.30 | Develop a periodic sidewalk maintenance program to ensure trip hazards in the pedestrian path of travel are eliminated. | In Planning Process (Community Management is facilitating)
A.31 | Add 5-foot sidewalk on Los Trancos Drive between Locke Court and Harvey Court. | Future Fiscal Year TBD
A.32 | Add 5-foot sidewalk on Los Trancos Drive between Gibbs Court and Blake Court. | Future Fiscal Year TBD
A.33 | Conduct a detailed analysis of providing a 5-foot sidewalk on the southerly side of Vista Bonita Drive. | Future Fiscal Year TBD
A.34 | Add an additional streetlight at the un-controlled mid-block crossing on Vista Bonita Drive to increase pedestrian visibility at night. | In Planning Process (bidding is in process; expected early 2019)
A.35 | Install in-pavement flashers with pedestrian push button activation on both sides of the crossing on Vista Bonita Drive. | Future Fiscal Year TBD
A.36 | Remove the curb adjacent landscaped areas on the westerly side of Gabrielino Drive north of Vista Bonita Drive. | Future Fiscal Year TBD